## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Research data points on tablets installation process | Important to be aware of tablets installation process | 2023-01-01 | 2023-02-01
Interview staff regarding their knowledge about this technology | All of the staff must be aware of tablets functionality | 2013-02-01 | 2023-02-01
Define Tablet Installation Scope | Location where the tablets are installed | 2023-02-01 | 2023-03-01
Coordinate electrician scheduling | Wired the tablets to keep them charged | 2023-03-01 | 2023-04-01
Staff training plan | Trained staff on new systems | 2023-03-01 | 2023-06-01
Real time menu update process | Continously update items on menu | 2023-08-01 | 2023-10-01
Customizing and branding | Look of the menu site | 2023-10-01 | 13/1/23
Implementation of service efficiency metrics | Mterics to measure the service efficiency | 13/1/23 | 16/1/23
Customer satisfaction improvement plan | Efficient customer retention rate | 18/1/23 | 23/1/23
Optimization of ordering processing time | Order time must be reduced | 23/1/23 | 26/1/23
Waste reduction strategy implementation | Wastage of food is minimized | 27/1/23 | 31/1/23
Average sales increase plan | Increase the annual revenue | 2023-01-02 | 15/2/23

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
#NAME?
Gather historical data on tablet launch |  | 3 | 3 | 5 | 6 | H
Create contracts and statements of work for vendors |  | 2 | 2 | 6 | 8 | H
Create project charter |  | 4 | 4 | 8 | 10 | H
Milestone 2: Tablets and Accessories
Tablets research |  | 2 | 2 | 3 | 4 | H
Select Tablet vendors |  | 1 | 1 | 3 | 4 | H
Compare tablet pricing and specifications |  | 1 | 1 | 2 | 5 | H
Milestone 3: Planning
Develop a plan |  | 3 | 3 | 5 | 8 | H
Send menu items and coupon values to the designer |  | 1 | 1 | 3 | 5 | H
Update POS system | If older version is installed in the tablets than it would take extra time to install newer version | 2 | 2 | 5 | 7 | H
Electrician wire both locations | Check with electrician on whether mornings or afternoons work better with their schedule | 2 | 2 | 4 | 5 | M
Tablets preparation for deployment |  | 2 | 2 | 4 | 6 | H
Test the tablets | Test the tablets to make them error free | 2 | 2 | 4 | 5 | H
Milestone 4: Training
Training Schedule |  | 2 | 2 | 3 | 4 | H
Manager training |  | 3 | 3 | 5 | 7 | H
Staff training | Staff training is a difficult process and maybe it would take som extra time | 4 | 4 | 6 | 9
Milestone 5: Execution
Evaluation survey questions |  | 1 | 1 | 3 | 5 | H
Send invites to friends and families | Invite friends and families to check the tablets and staff performance | 0 | 0 | 1 | 2 | H
Test run on tablets with friends and families |  | 1 | 1 | 2 | 5 | H

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
Digital Menu Ordering | https://www.revolutionordering.com/blog/digital-menu-ordering | 2023-01-01 | The link provide useful information regarding menu orders
Restaurant POS Platform | https://www.revolutionordering.com/blog/restaurant-pos-platform | 2023-01-01 | The link provide useful information about POS

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Average ticket time | The amount of time between placing an order and delivering it to the table. And a good average is eight minutes for appetizers and 12-15 minutes for entrees | What is the average time for entrees and apetizers to be delivered on the table? How does current ticket time compare to the defined standards? | Average time for entrees and apetizers is 12 and 8 minutes. Because of the current ticket time reduction the overall progress will be increased. | FALSE
Check out time | one-minute checkout time and ensure the checkout process is seamless | How long does it take, on average, for customers to checkout? Have any customer reported difficulty in checkout process? | Customers should be checkout in less than 10 minutes. Take feedback from customers on the difficulty they met during checkout process. | FALSE
Technical issues reporting | Help customers have a positive and efficient experience, our goal is that less than 5% customers report technical issues each week. | Have any customer reported difficulty in placing order? Are the technical issue reporting is acceptable which is 5%? | Customers order place should reach your desired goal. By reaching this goal technical issue will be resolved. | FALSE
Order accuracy | Assuming the tablets function properly and aim for 98% order accuracy | What percentage of orders placed through the tablets have been accurate? Is the order accuracy meet our desired goal? | Percentage of accurate orders placed through tablets that should be 98%. The goal is the mission. | FALSE
Customer wait time | Aim for an average wait time of ten minutes or less before customers are seated, wait times to go down as table turn time decreases | What is the current wait time for customers in the lobby? How does the current wait time compare to the target of our goal? | The wait time should be less than 10 minutes. Comparison of actual wait time with the target of ten minutes | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Question Answer Options (depends on question type)
Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
During your visit, what did you order? Choose all that apply. | Multiple choice | Drinks | Appetizers | Dinner | Dessert
Did you use the tablet to put in multiple orders while you were dining? | Yes/No
On a scale of 1-5, please rate your experience with the tablet overall | Scaled | 1 - Lacking | 2 - Mediocre | 3 - Neutral | 4 - Good | 5 - Great
How well did your waiter instruct you how to use the tablet? | Scaled | 1 - Not well | 2 - OK | 3 - Very well
On a scale of 1-5, how easy was it to use the tablet navigation? | Scaled | 1 - Difficult | 2 - Slightly difficult | 3 - Neutral | 4 - Fairly easy | 5 - Very easy
How easy was it to order directly from the menu on the tablet? | Scaled | 1 - Difficult | 2 - Slightly difficult | 3 - Neutral | 4 - Fairly easy | 5 - Very easy
On average, how long did you wait for your table? | Multiple choice | 0-5 min | 6-10 min. | 11-15 min. | 15+ min.
On average, how long did it take to receive your food order? | Multiple choice | 0-20 min. | 21-30 min. | 31-40 min. | 41-50 min. | 50+ min.
Did the kitchen prepare your order correctly? | Yes/No
If not, what went wrong? | Multiple choice | Wrong entree was brought out | Didn’t leave off the parsley | Didn’t leave off the cheese | Didn’t make the substitution I wanted | Entree was overcooked
How would you respond to the following sentence: “I found the checkout process quick, easy, and secure.” | True/False
How confident are you in submitting your payment through a tablet? | Scales | Not at all | Somewhat | Neutral | Confident | Very confident
Did you have any technical issues with your tablet? | Yes/No
The rating of overall experience with the tablet. | Multiple choice | Laking | Mediocre | Neutral | Good | Great