## Retrospective Ideas
Feedback From: | Type: | Description: | Evidence: | Actions:
Customers | Went well | 82% of guests ordered appetizers through the tablet, indicating a positive response to the ordering experience.
Customers | Needs improvement | 12% reported technical issues, including screen freezing and glitches, highlighting the need to address and minimize such disruptions.
Customers | Went well | 78% signed up for the newsletter, and 16% joined the Birthday Club through the tablet, showcasing effective integration of promotional features.
Customers | Needs improvement | 28% experienced order inaccuracies, emphasizing the importance of improving accuracy to prevent customer dissatisfaction.
Customers | Went well | 82% found the checkout process quick, easy, and secure, reflecting a positive perception of the tablet's efficiency.
Customers | Needs improvement | While 40% favored the tablet experience, 30% preferred a mix of tablet and waiter interaction, suggesting the need for flexible ordering options to accommodate diverse preferences.
Project team | Went well | Alex and Gilly reported successful tablet installations at their respective locations.
Project team | Needs improvement | One area we could still improve is table turn time
Project team | Went well | Weekly vendor calls, as noted by Peta, facilitated clear communication and task coordination.
Project team | Needs improvement | Few technical issues during the POS integration process, so it needs to be improved.
Project team | Went well | Weekly vendor calls, as noted by Peta, facilitated clear communication and task coordination.
Project team | Needs improvement | Alex, Gilly, and Zane highlighted challenges with table turn time and food order accuracy.